## Sheet1
| Task Name | Start | End | Allocation | Duration (days)
Week 6 Preliminary Release
| Validation Testing Strategy | 2018-02-07 | 2018-02-14 | Steven | 7
| JUnit Testing Strategy | 2018-02-10 | 2018-02-17 | Liam, Sandy | 7
| Updated Project Plan | 2018-02-14 | 2018-02-16 | Chris | 2
| Executables for 4 Prototypes | 2018-02-10 | 2018-02-21 | Elias, Steven, Sandy, Chris | 11
| Main Gizmoball Code - Final Implementation | 2018-02-21 | 2018-03-21 | All | 28
| have friction, gravity and velocity enabled and working | 2018-03-21 | 2018-03-03 | Steven, Chris & Elias | 10
| Integrate Absorber prototype into main implementation | 2018-02-21 | 2018-03-07 | Chris, Elias, & Steven | 14
| Integrate saving and loading prototype into implementation | 2018-02-21 | 2018-03-14 | All | 21
| Integrate collsion details into implementation | 2018-02-21 | 2018-03-07 | Chris, Elias, Steven & Sandy | 14
| have key listener for flipper working | 2018-02-21 | 2018-03-10 | Liam, Sandy | 17
| Have flipper movement and flipper collsions complete21/02/2018 |  | 2018-03-10 | Sandy & Liam | 17
| attach listeners to build mode buttons communicating with model | 2018-02-21 | 2018-03-10 | Steven & Chris | 17
| attach listeners to gameplay buttons communicating with model | 2018-02-21 | 2018-03-14 | Sandy & Liam | 21
| have all other listeners implemented | 2018-03-03 | 2018-03-19 | All | 16
| have Build mode gui interface button functionality complete | 2018-02-21 | 2018-03-14 | All | 21
| Complete implementation of build mode grid and game boundary | 29/02/2018 | 2018-03-16 | All | 17
| model classes including gizmos, ball, collisions etc complete | 2018-02-21 | 2018-03-20 | All | 27
| complete the run mode GUI and key interactions | 2018-02-21 | 2018-03-18 | All | 25
| Add Ball collisions colour effects | 2018-03-14 | 2018-03-19 | All | 5
| generate final class diagram with methods and associations | 2018-03-21 | 2018-03-22 | Steven | 1
Week 10 Final Deadline | Critique and Demonstration | 2018-03-20 | 2018-03-21 | All | 1
Design
Testing Strategy & Prototyping
Implementation, Critique and Demonstration