## Sheet1
| Task Name | Start | End | Allocation | Duration (days)
Week 3 Preliminary Design Deadline
| Final Design | 2018-01-31 | 2018-02-10 | All | 10
| Validation Testing Strategy | 2018-02-07 | 2018-02-14 | Steven | 7
| JUnit Testing Strategy | 2018-02-10 | 2018-02-17 | Liam, Sandy | 7
| Updated Project Plan | 2018-02-14 | 2018-02-16 | Chris | 2
Week 6 Preliminary Release Deadline | Executables for 4 Prototypes | 2018-02-10 | 2018-02-21 | Elias, Steven, Sandy, Chris | 11
| Java Implementation | 2018-02-21 | 2018-03-21 | All | 28
Week 10 Final Deadline | Critique and Demonstration | 2018-03-20 | 2018-03-21 | All | 1
Design
Testing Strategy & Prototyping
Implementation, Critique and Demonstration